## Assumptions
Voice Stage — Assumptions
Blue cells are inputs. Edit them to flex the model.
Rates
Founder review rate (USD/hr) | 50 | USD/hr | Your opportunity cost
Mid-senior backend (MX, USD/hr) | 30 | USD/hr | Reference; not used in this plan
Mobile contractor (LATAM, USD/hr) | 90 | USD/hr | Reference; used in optional 'human Phase 3' scenario
Claude API — build
Sonnet 4.6 input ($/1M tok) | 3 | USD
Sonnet 4.6 output ($/1M tok) | 15 | USD
Haiku 4.5 input ($/1M tok) | 0.8 | USD
Haiku 4.5 output ($/1M tok) | 4 | USD
Build tokens per Claude-hour (K) | 25 | K tokens | Agentic-coding throughput
Build I/O split (input share) | 70% | % | Code reads vs writes
Voice runtime — per active tester
Active testers (count) | 8 | count | Mid of 5-10
Voice minutes per tester per day | 6 | min | Real-world conversational use
Active days per month | 16 | days | Working days actually using
Avg Claude tokens per voice turn | 1800 | tokens | Haiku-dominant
Voice turns per minute | 1.4 | count | User+agent speech, alternating
Sonnet share of voice turns | 10% | % | Escalations only
Haiku share of voice turns | 90% | % | Default tier
Deepgram Nova-2 ($/min) | 0.0043 | USD/min | es-MX streaming
ElevenLabs Flash ($/1K chars) | 0.3 | USD | Multilingual es-MX
Chars per voice reply | 220 | count | Avg agent reply length spoken
Cloud / SaaS (monthly)
Fly.io (compute + Postgres + Redis) | 130 | USD/mo | Larger than MVP — voice gateway + websockets
Domain + Cloudflare | 2 | USD/mo
Auth0 (B2C essentials) | 25 | USD/mo | Phone OTP needs paid plan above free
Langfuse self-hosted on Fly | 25 | USD/mo | Slightly bigger VM
Sentry team plan | 25 | USD/mo | Mobile crash reporting included
WhatsApp Cloud (first 1K conv free) | 0 | USD/mo | Then $0.005-0.02/conv
Twilio SMS fallback | 25 | USD/mo | MX A2P
S3/Tigris audit (WORM) | 8 | USD/mo | 7-year retention starts small
Mobile EAS Build (Expo) | 19 | USD/mo | Hobby plan covers TestFlight builds
Apple Developer Program (amortized) | 9 | USD/mo | $99/yr ÷ 12
Google Play Console (amortized) | 2 | USD/mo | $25 one-time, amortized
Buffers
Engineering buffer % | 20% | % | +20% on top of estimates
API spend buffer % | 50% | % | +50% on top of token estimates

## Workstreams
Workstreams — Build Cost per Item
Phase-grouped. Claude does the engineering; you review and integrate.
Phase | Workstream | Pri | Claude h | Founder h | API cost | Founder cost | Total | Notes
1 | Repo bootstrap, CI, secrets, Fly account, domain | MUST | 6 | 2 | 1.485 | 120 | 121.485 | GitHub repo, EAS workspace, fly orgs, Cloudflare zone, DNS.
1 | Port domain services (listings/matching/scheduling/documents/payments/comms) | MUST | 18 | 4 | 4.455 | 240 | 244.455 | Mostly verbatim from MVP; lift SQLite→Postgres+pgvector for listings.
1 | Postgres + Redis on Fly with managed connection pooling | MUST | 8 | 2 | 1.98 | 120 | 121.98 | pgvector enabled, prisma-style migrations checked into repo.
1 | Orchestrator → Claude Agent SDK harness (realestate + locator + audit) | MUST | 22 | 6 | 5.445 | 360 | 365.445 | The core SDK migration. Carries the 161 assertions as the contract.
1 | Hooks: pii_redaction, spend_caps, audit_log, trace_emit | MUST | 10 | 3 | 2.475 | 180 | 182.475 | Presidio + es-MX NER; per-tenant per-day caps; WORM audit emit.
1 | Streaming endpoint /agent/run/stream (SSE) | MUST | 6 | 2 | 1.485 | 120 | 121.485 | Token-level events compatible with voice gateway.
1 | Adapt 161 assertions to SDK behavior contract | MUST | 10 | 3 | 2.475 | 180 | 182.475 | Preserve every existing test; add streaming + hook tests.
2 | voice-gateway scaffold (FastAPI + WebSocket) | MUST | 6 | 2 | 1.485 | 120 | 121.485 | Accept/return bidirectional audio + control JSON.
2 | Deepgram Nova-2 es-MX streaming adapter | MUST | 6 | 2 | 1.485 | 120 | 121.485 | WS client; partial→final reroute; VAD-based end-of-speech.
2 | ElevenLabs Flash streaming TTS adapter | MUST | 6 | 2 | 1.485 | 120 | 121.485 | TTS-friendly phrase chunking; pause for tool calls.
2 | Pipeline orchestrator (STT→agent→TTS bridge) | MUST | 8 | 3 | 1.98 | 180 | 181.98 | Latency budget enforcement; backpressure handling.
2 | Barge-in + cancel + WS reconnect logic | SHOULD | 8 | 3 | 1.98 | 180 | 181.98 | VAD on inbound mic while TTS playing; <200ms cancel.
2 | Latency benchmarks + load tests | MUST | 4 | 2 | 0.99 | 120 | 120.99 | k6 or locust; record P50/P95 against orchestrator.
3 | RN + Expo app scaffold, navigation, theme, i18n (es-MX) | MUST | 10 | 3 | 2.475 | 180 | 182.475 | expo-router, Zustand, react-i18next.
3 | Voice components: MicButton, waveform, audio capture/playback | MUST | 14 | 5 | 3.465 | 300 | 303.465 | expo-av + custom Audio classes; haptic feedback.
3 | VoiceClient (WS bridge) + reconnect + auth attach | MUST | 8 | 3 | 1.98 | 180 | 181.98 | Token attached to handshake; resumes within 1s on drop.
3 | Card components: ListingCard, SlotCard, AuditCard, AgentChips | MUST | 10 | 3 | 2.475 | 180 | 182.475 | Visual feed below the mic; tap focuses next turn.
3 | Screens: Onboarding, Home, ListingDetail, VisitSchedule, AuditView | MUST | 12 | 4 | 2.97 | 240 | 242.97 | Minimum viable screen set per Phase 3.
3 | SessionTrace screen (in-app /agents.html equivalent) | SHOULD | 6 | 2 | 1.485 | 120 | 121.485 | LFPDPPP-visible decision log; shareable for support.
3 | iOS build to TestFlight + Android internal track | MUST | 6 | 3 | 1.485 | 180 | 181.485 | EAS profiles; first device install; review pre-checks.
4 | identity service (Auth0 phone OTP + tenant + user model) | MUST | 12 | 4 | 2.97 | 240 | 242.97 | Phone OTP for buyers, magic link for realtors/owners.
4 | LFPDPPP consent flow + Aviso de Privacidad | MUST | 6 | 3 | 1.485 | 180 | 181.485 | Voice-accept option; consent record + audit-logged.
4 | DSAR endpoint (data export within 20 business days) | MUST | 4 | 2 | 0.99 | 120 | 120.99 | /api/identity/dsar/export; ZIP of all the user's data.
4 | Real WhatsApp Cloud API + template registration | MUST | 8 | 3 | 1.98 | 180 | 181.98 | Template approval flow; opt-in; 24h window; SMS fallback.
4 | S3/Tigris WORM audit chain + LFPIORPI report job | MUST | 6 | 3 | 1.485 | 180 | 181.485 | Hash-chained append-only; monthly UIF report generator.
4 | Sentry + Langfuse live for backend + mobile | MUST | 4 | 2 | 0.99 | 120 | 120.99 | Crash reports + AI traces before first tester logs in.
4 | Tester onboarding pack + invite codes + welcome flow | MUST | 6 | 3 | 1.485 | 180 | 181.485 | 8-page PDF in es-MX; NDA; support contact; tutorial.
4 | 3 internal testers full flow over 48h + bug bash | MUST | 4 | 8 | 0.99 | 480 | 480.99 | Real devices, real LTE in CDMX; document P0/P1/P2.
| TOTAL |  | 234 | 87 | 57.915 | 5220 | 5277.915
| Phase 1 |  | 80 | 22 | 19.8 | 1320 | 1339.8
| Phase 2 |  | 38 | 14 | 9.405 | 840 | 849.405
| Phase 3 |  | 66 | 23 | 16.335 | 1380 | 1396.335
| Phase 4 |  | 50 | 28 | 12.375 | 1680 | 1692.375

## Runtime
Runtime — Monthly Cost During Testing
Formula-driven from Assumptions.
Item | USD / mo | Notes
Voice volume metrics
Voice minutes per month | 768 | testers × min/d × days/mo
Voice turns per month | 1075.2
Spoken reply characters per month | 236544
AI tokens (Claude)
Sonnet $ (60% in / 40% out) | 2.2644
Haiku $ (60% in / 40% out) | 5.4345
Voice STT / TTS
Deepgram STT (Nova-2 es-MX) | 3.3024
ElevenLabs Flash TTS (es-MX) | 70.9632
AI + Voice subtotal | 81.9645
Cloud + SaaS
Fly.io | 130
Domain + Cloudflare | 2
Auth0 | 25
Langfuse | 25
Sentry | 25
WhatsApp Cloud | 0
Twilio SMS | 25
S3/Tigris WORM | 8
Expo EAS Build | 19
Apple Developer (amort) | 9
Google Play (amort) | 2
Cloud + SaaS subtotal | 270
TOTAL monthly burn while testing | 351.9645
Per-tester per-month | 10.2456 | Variable AI + voice per tester

## Phase Plan
8-Week Phase Plan
Costs roll up from Workstreams via SUMIF on phase number.
Phase | Weeks | Theme | Claude h | Founder h | Cost | Exit criteria
Phase 1 | 1-2 | Backend on the SDK harness | 80 | 22 | 1339.8 | Services on Fly; orchestrator on Claude Agent SDK; 161+ tests green; SSE stream live.
Phase 2 | 3-4 | Voice gateway service | 38 | 14 | 849.405 | WS audio in/out; Deepgram+ElevenLabs; P50 latency ≤ 1.5s; barge-in works.
Phase 3 | 5-6 | Mobile app skeleton (RN + Expo) | 66 | 23 | 1396.335 | iOS + Android builds; mic + speaker; PTT UX; cards render; E2E flow on real device.
Phase 4 | 7-8 | Identity + compliance + tester onboarding | 50 | 28 | 1692.375 | Phone OTP; LFPDPPP consent; DSAR; WA Cloud; audit trail; 3 testers signed off.
TOTAL | 1-8 | Stage + testers | 234 | 87 | 5277.915 | Ready for external testers

## Summary
Voice Stage — Cost Summary
All numbers are formulas. Edit Assumptions to flex.
| Value | Notes
Build (Claude does engineering, you review)
Claude hours total | 234
API spend (Sonnet-priced) | 57.915
Your review + integration cost | 5220
Build TOTAL one-time | 5277.915
Runtime while testing
Monthly burn | 351.9645 | All-in
3-month testing window | 1055.8934
Build + 3 months | 6333.8084
Reference — same scope with humans (no Claude)
If MX backend engineer does the work | 10152 | Reference: in-house cost only
If mobile contractor does Phase 3 only | 5940 | Reference: hire a RN contractor for the app work
Savings — Claude path vs MX engineer | 4874.085
Per-tester economics
AI + voice variable cost / tester / month | 10.2456 | Token + STT + TTS only
All-in cost / tester / month (incl. cloud + SaaS) | 43.9956 | What it costs to keep one tester active

## Decision Gates
Decision Gates — Pre-committed Go/No-Go
Use these instead of arguing in the moment.
When | Decision | If no — what to cut
End of Week 1 | SDK harness passing ported 161 tests? | Slip Week 2; don't start streaming on red tests.
End of Week 2 | Streaming endpoint emitting hooks correctly? | Defer barge-in to Week 4; keep voice simpler.
End of Week 3 | Deepgram + ElevenLabs latency ≤ 1.5s locally? | Downgrade to Cartesia TTS; accept higher latency for first wave.
End of Week 4 | Voice gateway stable under barge-in + reconnect? | Ship without barge-in; testers will tolerate; fix in Week 7 slack.
End of Week 5 | iOS build on real device with audio working? | Deprioritize Android; ship iOS-first to smaller cohort.
End of Week 6 | E2E voice flow hits 1.5s P50 on real LTE? | If 1.8-2.0s, ship; if >2.5s, MX-region edge or Haiku-only routing.
End of Week 7 | LFPDPPP review clean, Auth0 sufficient? | Swap Auth0→Cognito (1-day pivot); defer LFPDPPP polish 3 days.
Mid Week 8 | Three internal testers comfortable? | Delay external testers 1 week; better than poisoning first impression.